Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 28 October 2026 |
| --- | --- |
| Team ID | To be filled by team |
| Project Name | Healthcare Risk Analysis Dashboard using Tableau |
| Maximum Marks | 8 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create the product backlog and sprint schedule for the Healthcare Risk Analysis Dashboard. Story points are planning estimates; team names and actual completion values should be updated by the team.

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Data Preparation | USN-1 | As a project analyst, I want to connect the healthcare CSV and validate field types so that the dashboard uses reliable data. | 3 | High | Team member(s) TBD |
| Sprint-1 | KPI Overview | USN-2 | As a dashboard user, I want to see total records and counts for heart disease, diabetes and stroke so I can understand the dataset quickly. | 3 | High | Team member(s) TBD |
| Sprint-1 | Demographic Analysis | USN-3 | As an analyst, I want to compare disease labels by age group and gender so I can explore demographic patterns. | 5 | High | Team member(s) TBD |
| Sprint-2 | Clinical Indicators | USN-4 | As an analyst, I want to compare BMI, blood pressure, cholesterol and glucose with disease labels using appropriate aggregations. | 5 | High | Team member(s) TBD |
| Sprint-2 | Lifestyle Analysis | USN-5 | As an analyst, I want to compare smoking, alcohol and exercise categories with disease labels to explore associations. | 5 | Medium | Team member(s) TBD |
| Sprint-2 | Symptoms Analysis | USN-6 | As an analyst, I want to explore fatigue, chest pain and dizziness by disease status using clear count or percentage charts. | 3 | Medium | Team member(s) TBD |
| Sprint-3 | Interactive Dashboard | USN-7 | As a dashboard user, I want filters for gender, age group, smoking and exercise so I can focus on relevant segments. | 5 | High | Team member(s) TBD |
| Sprint-3 | Dashboard Design | USN-8 | As a reviewer, I want a well-organized dashboard with KPI cards, consistent colors, labels and tooltips so results are easy to interpret. | 5 | High | Team member(s) TBD |
| Sprint-4 | Quality Assurance | USN-9 | As a project reviewer, I want KPI values and chart aggregations checked against the source data so the dashboard is dependable. | 3 | High | Team member(s) TBD |
| Sprint-4 | Documentation & Delivery | USN-10 | As a project team, we want to document limitations and prepare the final Tableau workbook and project report for submission. | 3 | Medium | Team member(s) TBD |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 11 | 6 Days | 29 Oct 2026 | 03 Nov 2026 | TBD | TBD |
| Sprint-2 | 13 | 6 Days | 05 Nov 2026 | 10 Nov 2026 | TBD | TBD |
| Sprint-3 | 10 | 6 Days | 12 Nov 2026 | 17 Nov 2026 | TBD | TBD |
| Sprint-4 | 6 | 6 Days | 19 Nov 2026 | 24 Nov 2026 | TBD | TBD |

Velocity:

Planned velocity estimate: 40 story points across 4 sprints gives an average of 10 story points per sprint. For a 6-day sprint, planned throughput is about 1.67 story points per day. This is only an estimate; update it using actual completed points.

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts

Planned Burndown Guide (Sprint-1)

Illustrative planned remaining work for Sprint-1 (11 story points). Replace the planned values with actual remaining work at the end of each day.

| Sprint Day | Ideal Remaining Story Points | Actual Remaining Story Points |
| --- | --- | --- |
| Day 1 | 9.2 | TBD |
| Day 2 | 7.3 | TBD |
| Day 3 | 5.5 | TBD |
| Day 4 | 3.7 | TBD |
| Day 5 | 1.8 | TBD |
| Day 6 | 0 | TBD |

Planning Notes

• Story points are planning estimates, not measured completion.

• Team member names are placeholders because names were not provided.

• Actual completed points and release dates are marked TBD; update them after each sprint rather than inventing results.

• The dashboard is for descriptive analysis of the supplied healthcare dataset, not clinical diagnosis.

• Data-quality check: health_risk_score was previously observed as constant at 100 in the supplied dataset; verify its meaning before using it for risk ranking.